## Waterfall Estimation
|  |  |  | 2020 | [6 empty] | 2021
Internal Resources | Acct Type | Label | May | June | July | August | Sepbember | October | November | December | January | February | March | April | May | June
Project Manager | Operating | Hours | 160 | 100 | 80 | 80 | 100 | 40 | 40 | 40 | 40 | 80 | 100 | 80 | 80 | 100
|  | Value | 12800 | 8000 | 6400 | 6400 | 8000 | 3200 | 3200 | 3200 | 3200 | 6400 | 8000 | 6400 | 6400 | 8000
PMO Support | Operating | Hours |  | 25 | 20 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 200
|  | Value |  | 1750 | 1400 | 1400 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 11200 | 14000
TOTAL OPERATING |  |  | 12800 | 9750 | 7800 | 7800 | 9750 | 3200 | 3200 | 3200 | 3200 | 6400 | 8000 | 17600 | 17600 | 22000
Business Analyst | Capital | Hours |  | 200 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 100 | 80 | 80 | 100
|  | Value |  | 18000 | 14400 | 14400 | 14400 | 7200 | 7200 | 7200 | 7200 | 7200 | 9000 | 7200 | 7200 | 9000
Software Developer (Integration) | Capital | Hours |  | 25 | 20 | 20 | 25 | 160 | 160 | 160 | 160 | 80 | 100 | 0 | 0 | 0
|  | Value |  | 1125 | 900 | 900 | 1125 | 7200 | 7200 | 7200 | 7200 | 3600 | 4500 | 0 | 0 | 0
Software Developer (Security Protocol) | Capital | Hours |  | 25 | 20 | 20 | 25 | 160 | 160 | 160 | 160 | 80 | 100 | 0 | 0 | 0
|  | Value |  | 1125 | 900 | 900 | 1125 | 7200 | 7200 | 7200 | 7200 | 3600 | 4500 | 0 | 0 | 0
Quality Assurance | Capital | Hours |  | 100 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 160 | 200 | 0 | 0 | 0
|  | Value |  | 4500 | 3600 | 3600 | 3600 | 0 | 0 | 0 | 0 | 7200 | 9000 | 0 | 0 | 0
TOTAL CAPITAL |  |  |  | 34500 | 27600 | 27600 | 30000 | 24800 | 24800 | 24800 | 24800 | 28000 | 35000 | 24800 | 24800 | 31000
Capital Expenditures |  |  |  | June | July | August | Sepbember | October | November | December | January | February | March | April | May | June
PMO Vendor Software Purchase | Capital
PMO Vendor license | Capital
PMO Vendor Milestone Delivery | Capital
Laptop Purchases | Capital |  |  | 25000 | 25000 | 25000 | 25000
TOTALS
Operating Expenses |  |  |  | June | July | August | Sepbember | October | November | December | January | February | March | April | May | June
PMO Vendor Software license | Operating
Termination fee for previous PMO tool | Operating | [8 empty] | 1000 | [5 empty] | 1000
In-Person Conferences | Operating |  | 10000 | [7 empty] | 10000
TOTALS

## Fiscal Calendar
Based on 2020 Calendar
Month | Time Range | # of Weeks
January | 1/1 thru 1/25 | 4
February | 1/26 thru 2/22 | 4
March | 2/23 thru 3/28 | 5
April | 3/29 thru 4/25 | 4
May | 4/26 thru 5/23 | 4
June | 5/24 thru 6/27 | 5
July | 6/28 thru 7/25 | 4
August | 7/26 thru 8/22 | 4
September | 8/23 thru 9/26 | 5
October | 9/27 thru 10/24 | 4
November | 10/25 thru 11/21 | 4
December | 11/22 thru 12/26 | 5

## Original Budget
Project Investment | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | TOTALS
Capital
Hardware Purchase | 100000 | 100000 |  |  |  |  | 200000
Software Purchase | 100000 | 100000 |  |  |  |  | 200000
Software License | 50000 | 50000 |  |  |  |  | 100000
Vendor Expense | 125000 | 125000 |  |  |  |  | 250000
Internal Expense | 125000 | 125000 |  |  |  |  | 250000
Total Capital Expense | 500000 | 500000 | 0 | 0 | 0 |  | 1000000
Operating
Software License |  |  | 1000 | 1000 | 1000 |  | 3000
Internal Expense | 50000 | 50000 |  |  |  |  | 100000
Operate & Maintain | 0 | 0 | 10000 | 10000 |  |  | 20000
Time & Expense | 10000 | 10000 |  |  |  |  | 20000
Depreciation | 0 | 10000 | 10000 | 10000 | 10000 | 0 | 40000
Asset Write-Off | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Total Operating Expense | 60000 | 70000 | 20000 | 20000 | 10000 |  | 203000
TOTAL INVESTMENT | 560000 | 570000 | 20000 | 20000 | 10000 |  | 1203000

## Country Rates
Rates | Country
80 | United States
Canada
45 | Puerto Rico
Mexico
45 | Australia
Singapore
45 | China
Malaysia
India
90 | Switzerland
Norway
Netherlands
France
Belgium
Spain
Germany
United Kingdom
70 | Czech Republic
Hungary
Romania

## Waterfall Estimation Blank
|  |  |  | 2020 | [6 empty] | 2021
Internal Resources | Acct Type | Label | May | June | July | August | Sepbember | October | November | December | January | February | March | April | May | June
Project Manager | Operating | Hours | 40
|  | Value | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMO Support | Operating | Hours
|  | Value |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OPERATING |  |  | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours confirmed by resource or resource manager - just enter hours above | ---------> | 25% | Percentage allocation
|  | 40 | Working Hours per week
|  | 10 | Budgeted hours per week
|  | 40 | Budgeted hours per month
|  | 80 | Country Rate established
|  | 3200 | Cost Per Month