## Timesheet
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
Daniel Rivera | Phase | Allocation | Mon | Tue | Wed | Thu | Fri | TOTAL
Project #1 | Initiation | 40% | 4 | 3 | 3 | 3 | 3 | 16
Project #2 | Warranty | 40% | 3 | 4 | 4 | 2 | 3 | 16
Operate & Maintain | N/A | 5% | 1 | 0 | 1 | 0 | 0 | 2
Administration | N/A | 15% | 0 | 1 | 0 | 3 | 2 | 6
TOTALS |  | 100% | 8 | 8 | 8 | 8 | 8 | 40
Notes:
Each project you're assigned to will be listed.
Be honest when booking hours. Don't try to just meet budget goals. This provides accurate project data to Finance.
Hours booked for projects are closed at the end of the fiscal month.
Operate & Maintain is support activities you may do. Or, you may be assigned to an O&M project which supports operational improvements.
Administration includes non-project meetings, training, mentoring, or activities not related to projects or operational support.

## Internal Labor Dashboard
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
Project: | PMO Automation
Timeframe: | Jun, 2020
Resource | Account | Hours | Amount
Daniel Rivera | Operating | 25 | 2000
Rob Jones | Operating | 40 | 2800
John Roberts | Capital | 200 | 18000
Ludvig Luger | Capital | 25 | 1125
Lex Borga | Capital | 25 | 1125
Jake Studd | Capital | 100 | 4500
TOTALS |  | 415 | 25050
Notes:
At the end of the month, make sure hours and amount match up with budgeted hours for month. Compare with budget plan.
It's okay if hours are different as you want EXACT effort.
If it's early in the month, the hours will obviously be low.
Make sure resources are booking time!
Overbooking? Why are they working so much? Will schedule be impacted?

## PO Receipt
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
PO Number | PO Line Item | Project | Vendor | PO Line Description | Purchase Order | PO to Process | Month to Process | PO to Bill | Invoices Received | Finance Rep
PO0022347 | 00010 | PMO Automation | PMO Tools, Inc. | Project Kick-Off | 50000 | 50000 | Jun, 2020 | 0 | 50000 | Daniel Rivera
PO0022347 | 00020 | PMO Automation | PMO Tools, Inc. | Requirements Signoff | 100000 | 75000 | Sep, 2020 | 25000 | 0 | Daniel Rivera
PO0022347 | 00030 | PMO Automation | PMO Tools, Inc. | Development/Unit Testing | 100000 | 0 | Feb, 2021 | 100000 | 0 | Daniel Rivera
PO0022347 | 00040 | PMO Automation | PMO Tools, Inc. | User Testing / Defect Repair | 50000 | 0 | Mar, 2021 | 50000 | 0 | Daniel Rivera
PO0022347 | 00050 | PMO Automation | PMO Tools, Inc. | Production Rollout / User Training | 25000 | 0 | Jul, 2021 | 25000 | 0 | Daniel Rivera
Notes:
For each SOW, one master PO
For each deliverable, a unique PO
Line Description should match SOW milestones
PO is overall amount for deliverable
PO to process may be a fractional amount depending on work done
Month to Process is the fiscal month
PO to Bill is remaining PO to process
Invoices - makes sure that invoices are received. You can also dispute invoices if work is not done yet.
Finance Rep is the procurement or Finance person who can help you with questions.
Hardware purchase will re realized by invoices not PO dashboards

## Country Rates
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
Rates | Country
80 | United States
Canada
45 | Puerto Rico
Mexico
45 | Australia
Singapore
45 | China
Malaysia
India
90 | Switzerland
Norway
Netherlands
France
Belgium
Spain
Germany
United Kingdom
70 | Czech Republic
Hungary
Romania